Zimbabwe Action Plans (South Africa September, 2017)

| Data elements and indicators or other priorities |  | Key next steps/actions |  | Timeline | Lead agencies responsible for implementation (please be specific) |  |  | Anticipated Support Needed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Indicators not harmonised across departments in the Ministry |  | Harmonise indicators |  | Q1 2018 | MoHCC, Family Health Department |  |  | TA, Funding for stakeholders meetings |
| Current tools not capturing all child health indicators routinely |  | Revision of data collection tools and summary forms to capture important child health indicators routinely |  | Q1 2018 | MoHCC, Family Health Department |  |  | TA, Funding for stakeholders meetings |
| Zimbabwe has not adopted community management of pneumonia (CMP) |  | Advocate for CMP and develop guidelines and indicators. |  | Q2 2018 | MoHCC, Family Health Department |  |  | TA and funding for advocacy meetings. |
| Ministry has RMNCI Scorecard but missing some important child health indicators. |  | Review Scorecard and strengthen use at all levels |  | Q1 2017 | MoHCC, Family Health Department |  |  | Funding for meetings |
| Data elements and indicators or other priorities | Key next steps/actions |  | Timeline |  |  | Lead agencies responsible for implementation (please be specific) | Anticipated Support Needed |  |
| Recording and reporting for IMNCI is paper based | Develop module for IMNCI in the EHR. |  | Q4 2017 |  |  | MoHCC, Family Health Department working with Health Information Department | TA and Funding for meetings to develop module |  |
| Data elements and indicators for CHIS are not comprehensive enough (missing out key information on patient management) | Review data collection tools and align to reporting forms and DHIS2 |  | Q4 2017 |  |  | MoHCC, Family Health Department working with Health Information Department | Funding stakeholders meetings |  |
| No recent comprehensive assessment of NHIS and CHIS | Conducted NHIS and CHIS situation analysis using MEASURE models |  | Q2 2018 |  |  | MOHCC, Health Information Department | TA, Support for stakeholders meetings |  |
| Data elements and indicators or other priorities | Key next steps/actions |  | Timeline |  |  | Lead agencies responsible for implementation (please be specific) | Anticipated Support Needed |  |
| Lack of comprehensive standardised tools for community health workers | Scale up use of community register that was piloted in one province (Manicaland) |  | Q1 2018 |  |  | MoHCC, Family Health Department | Funding for stakeholders meetings, printing of registers and training on use |  |
| Currently community recording and reporting systems are paper based | Pilot use of digital systems to strengthen CHIS |  | Q2 2018 |  |  | MoHCC, Health Information Department | Funding to set up digital systems in pilot districts |  |