## Global Strategic Framework
Overall Aim: To contribute to reducing U5 mortality and morbidity by optimising the role of nutrition within iCCM in policy and practice
Outcome 1: Nutrition components of iCCM programmes are implemented systematically and effectively
Outcome 2: Global ICCM guidelines include treatment of acute malnutrition
| Objectives | Targets | Activities
Result 1 To consolidate, reinforce and promote the existing nutrition components of iCCM (e.g. nutrition counselling, screening and referral of acute malnutrition cases). | Map out the type of nutrition activities implemented as part of ICCM in different countries/contexts | Up to XX programs (Packages??) with integrated iCCM and nutrition strengthen activities are documented | IYCF programming?? Others?? Countries with iCCM and Nutrition plans
| Identify strength, weaknesses, ops and threats affecting the implementation of existing nutriton components of ICCM |  | Develop and/or strengthen technical guidance to optimise the implementation of nutrition components of iCCM interventions through documentation of best practice and development of tools
| Support the dissemination of experiences and lessons learned on iCCM and Nutrition | nutrition session in the next evidence review symposium | Research projects to collect evidence of the impact of integrating nutrition activities into iCCM are implemented
Result 2 To generate and promote evidence on the effectiveness, cost-effectiveness and impact of treating acute malnutrition through iCCM | To identify countries where the treatment of acute malnutrition can be integrated into ICCM programmes at scale | Up to 5 priority countries identified | Map out the number of countries in which acute malnutrition (MAM and/or SAM) is part of national or subnational ICCM programmes
Identify opportunities for integrating acute malnutrition into existing ICCM programmes at scale
Identify funding needs and sources to support the integration of acute malnutrition into existing ICCM programmes at scale
| To ensure global and national level support for the integration of acute malnutrition treatment into ICCM programmes | Agreed list of evidence needs on ICCM and acute malnutrition treatment Operational manual/toolkit/training material on integrating acute malnutrition into ICCM programmes 10 peer-reviewed papers on ICCM and acute malnutrition treatment | Identify evidence-base necessary at a global level
Jointly identify evidence needs with national health authorities and other stakeholders
Develop and implement reseach programmes to generate the necessary evidence to address evidence gaps
| To influence global and national ICCM stakeholders to support the integration of acute malnutrition into ICCM policies | 3 national stakeholders develop tools with AM included in iCCM policies Up to two national guidelines recommend the integration of AM into iCCM | Strengthen coordination between nutrition and iCCM programmes to have common advocacy messages and to influence decission making process

## Subgroup Workplan
Result | Activities | Specific Activity | Countries | Lead Partners (&Contributors) | Time Frame | Outputs & Success Criteria | Progress (to May 2016) | Next Steps
Result 1 To consolidate, reinforce and promote the existing nutrition components of iCCM (e.g. nutrition counselling, screening and referral of acute malnutrition cases). | IYCF programming?? | 1) Document if advising on continued feeding is being done 2) Document if advising on feeding the sick child is effective at changing behaviour 3) Expand advising to IYCF counselling | DRC | MCSP - PATH and JSI can contribute | 2017
| Develop and/or strengthen technical guidance to optimise the implementation of nutrition components of iCCM interventions through documentation of best practice | 1) Technical recomendations on task shifting activities 2) CHWs examples 3) Lessons learned from other iCCM intervention that did not work (learning for nutrition acitivities) 4)Document the obstacles to effective advising | DRC ( 1, 2, 3) | MCSP - PATH and JSI can contribute | 2017
| Research projects to collect evidence of the impact of integrating nutrition activities into iCCM are implemented | ?? | DRC | MCSP - PATH and JSI can contribute | 2017
| Integrating preventive and curative aspects of nutriiton into iCCM programming (including IYCF) | 1) Examine IYCF practices and associated behaviors, provider counseling and care seeking practices for child health and nutrition, within the context of cultural beliefs and perceptions 2) ascertain the role of key influential members of the community on nutrition and child health practices 3) Examine feasibility of integrating preventive and curative aspects of nutrition into the iCCM program | DRC | PATH and JSI - Maternal and Child Survival Program- MCSP) | April- December 2016 | Conduct formative research used to design program in DRC, develop protocol, and tools and implement formative work | Protocol and tools developed | USAID review and IRB approval
Result 2 To generate and promote evidence on the effectiveness, cost-effectiveness and impact of treating acute malnutrition through iCCM | Map out the number of countries in which acute malnutrition (MAM and/or SAM) is part of national or subnational ICCM programmes | Through a methology based on desk reviews and key informants interviews document document iCCM in relation to nutrition, field examples and list of countries in which AM treatment and iCCM are integrated | Global | ACF (CMAM Forum) | 2016-07-01 | create a list of countries in which AM treatment and iCCM are integrated | Tor created and announce in relevant website | Select and contract external consultant
| Identify opportunities for integrating acute malnutrition into existing ICCM programmes at scale | 1)Develop a proposal together with all stakeholders and partners from Mali 2) Present this proposal to key donors 3) Obtain funds to develop the scaling up | Mali | ACF | 2016-07-01 | Get proposal funded | Consultation in Mali done | Present proposal to donors
|  | 1) Contact partnrs and stake holders to understand and document the current situation and interstes in SL 2) Explore the donors interest in Sierra Leone to introduce malnutrition treatment in iCCM programs 3) Create a working group with agencies working in SL | Sierra Leone | ACF & UNICEF
| Identify funding needs and sources to support the integration of acute malnutrition into existing ICCM programmes at scale | 1) Explore the potential of Power of Nutrition to support scalign up in Mali 2) Identify additional sources such as UNITLIFE | Mali | ACF & UNICEF ACF and Mali MoH | 2016-06-01
|  | work with countries that have expressed interest in applying for Global funds to support iCCM+Nut activities | Mali and others
| Identify evidence-base necessary at a global level | Continue to develop and prioritise research questions that the subgroup thinks need to be answered. | Global | All | 2015-12-01 | Document the list of research questions | completed | List the evidence gaps completed
| Jointly identify evidence needs with national health authorities and other stakeholders | Develop a list of priorities to generate evidence for iCCM and Nutrition in Kenya | Kenya | ACF & Save the Children | 2016-07-01 | Develop a research protocol | initial contacts done | stakeholder meeting in Nairobi in may&June
| Develop reseach projects to generate the necessary evidence to address evidence gaps | Implement different research projects through a consortium approach to better generate evidence in the different populations and contexts of Kenya | Kenya | ACF, Save the Children, UNICEF, WFP | 2017-01-01 | Implementation starts at field level
|  | Formative resarch on nutrition integration into iCCM (IYCF, refer and treatment for child illness, malnutrition) | DRC | PATH, JSI (through MCSP) | estimated July/August 2016 | data collection begins
|  | Develop the simplified algorithm and low-literacy tools as part of iCCM. Implement research on feasibility and acceptability of treatment by low-literate iCCM providers (phase 1). Develop RUTF supply chain eco-system. Implement research on impact and cost-efficiency (phase 2) | South Sudan | IRC | Phase 1 - now until 12/17 Phase 2 - late 2017 - 2018 | Phase 1 currently funded. Results of phase 1 study plus finalization of tools and treatment algorithm. Secure phase 2 funding.
| Strengthen coordination between nutrition and iCCM programmes to have common advocacy messages and to influence decission making process | Continioulsy influence international forum by presenting resuts of programs integrating iCCM and nutrition activitites | US & others | ALL |  |  | presented at GNR | presnet at Core group of Nutrition
Develop key advocacy documents and products that will influence decission making processes
|  | Include iCCM and nutrition topics in key global documents and strategies by participating in key reviews and technical advisory groups | Global